## Gantt Chart
GANTT CHART
PROJECT TITLE |  | POS - Power House Phitness (PHP) |  |  |  |  | ORGANIZATION NAME | [6 empty] | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE | [6 empty] | 2022-10-24
GROUP LEADER |  | Charles Olinsky
GROUP MEMBERS |  | Erica Dubie, Beesanne Kurzum, Olamide Kumapayi, Christina Rodriguez
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 9/8/2022 |  |  |  |  | W2 9/15/2022 |  |  |  |  | W3 9/22/2022 |  |  |  |  | W4 9/29/2022 |  |  |  |  | W5 10/6/2022 |  |  |  |  | W6 10/10/2022 |  |  |  |  | W7 10/17/2022 |  |  |  |  | W8 10/24/2022 |  |  |  |  | W9 10/31/2022 |  |  |  |  | W10 11/7/22 |  |  |  |  | W11 11/14/2022 |  |  |  |  | W12 11/21/2022 |  |  |  |  | W13 11/28/2022 |  |  |  |  | W14 12/5/2022
1 | Proct Conception and Initiation | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1.1 | Setting up Github | All | 2022-09-05 | 2022-09-05 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
1.1.1 | Setting up Discord | All | 2022-09-05 | 2022-09-05 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
1.2 | Setting up XAMPP | All | 2022-09-06 | 2022-09-08 | 2 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
1.3 | Assigning Group Leader | All | 2022-09-06 | 2022-09-06 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
1.4 | Deciding on a Concept | All | 2022-09-05 | 2022-09-05 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
1.5 | Create Directory Structure | Charlie | 2022-09-20 | 2022-09-20 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
1.6 | Clarify Concept - Fitness Center | All | 2022-09-26 | 2022-09-26 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
1.7 | Decide on Project Name | All | 2022-09-26 | 2022-09-26 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
| FINAL PRESENTATION SCRIPTS | All | 2022-11-21 | 2022-11-26 | 5 | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
Powerpoint | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2 | Planning
2.1 | Users - 3 classes | Christina |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.2 | Financial Reports - Z Reports - CashFlow | Christina |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.3 | Inventory - Details - Vendor - TTL | Beesanne |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.3.1 | Services | Erica, Charlie |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.4 | Shopping Cart - Payment | Olamide, Beesanne |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.5 | Reciepts | Olamide |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.6 | Security | Charlie |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.7 | Sessions Class | Charlie |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.8 | Data Management | Beesanne |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.9 | UI | Erica |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.1 | Email Notifications | Charlie |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
| Presentation Narration | Erica | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.11 | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
3 | Coding and Assembly
Charlie
Sessions Class
Intialize the Sessions class | bar: W6 10/10/2022 W to W7 10/17/2022 M
Meet with Denizard to discuss implementation | bar: W8 10/24/2022 R
Begin using HTTP Only Cookies in sessions | bar: W7 10/17/2022 W to W8 10/24/2022 M
Integrate Sessions into User Class | bar: W7 10/17/2022 W to W10 11/7/22 F
Integrate Sessions into Shopping Cart Class | bar: W8 10/24/2022 W to W10 11/7/22 F; W11 11/14/2022 T to W11 11/14/2022 F
Add Timeout method to the sessions class | bar: W9 10/31/2022 M to W10 11/7/22 M
Add Error Handling method to the sessions class | bar: W9 10/31/2022 M to W10 11/7/22 M
Integrate Sessions Class into User Class pt2 | bar: W11 11/14/2022 T to W11 11/14/2022 F
New sessions into account tab
Logout Function (in user profile)
Security
Begin Encrypting Data | bar: W6 10/10/2022 W to W7 10/17/2022 M
Create password hashing function | bar: W7 10/17/2022 W to W8 10/24/2022 M
Integrate Security and User Classes | bar: W9 10/31/2022 M to W10 11/7/22 F
Ensure safe queries | bar: W9 10/31/2022 M to W10 11/7/22 F
Protect against IP Spoofing | bar: W9 10/31/2022 M to W10 11/7/22 M; W11 11/14/2022 T to W11 11/14/2022 F
Implement Proper CSRF Protection | bar: W9 10/31/2022 M to W10 11/7/22 T
Christina
User Classes
Create Test Table PHPmyAdminj | bar: W6 10/10/2022 W to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
Implement SQL Queries in User Class Functions | bar: W6 10/10/2022 W to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
Test Creation of all 5 users | bar: W6 10/10/2022 W to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
error handeling | bar: W11 11/14/2022 T to W11 11/14/2022 F
connect to login | bar: W11 11/14/2022 T to W11 11/14/2022 F
roles class with access levels | bar: W8 10/24/2022 M to W9 10/31/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
php code for calculations | bar: W11 11/14/2022 T to W11 11/14/2022 F
User Class Method Functionality | bar: W8 10/24/2022 W to W9 10/31/2022 W; W11 11/14/2022 T to W11 11/14/2022 F
Finish createUser() function | bar: W10 11/7/22 M to W10 11/7/22 F; W11 11/14/2022 T to W11 11/14/2022 F
Add editUser() function | bar: W10 11/7/22 M to W10 11/7/22 F; W11 11/14/2022 T to W11 11/14/2022 F
Add deleteUser() Function | bar: W10 11/7/22 M to W10 11/7/22 F; W11 11/14/2022 T to W11 11/14/2022 F
Create Admin Page | bar: W11 11/14/2022 T to W12 11/21/2022 T
Financial Reports
Store Order History | bar: W11 11/14/2022 T to W11 11/14/2022 F
Different Report Types | bar: W11 11/14/2022 T to W11 11/14/2022 F
Service Reports | bar: W11 11/14/2022 T to W11 11/14/2022 F
Reports Tables | bar: W11 11/14/2022 T to W11 11/14/2022 F
Create Test Data | bar: W11 11/14/2022 T to W12 11/21/2022 F
Test Reporting Functions | bar: W11 11/14/2022 T to W12 11/21/2022 F
Generate Z-Report PDF | bar: W11 11/14/2022 T to W12 11/21/2022 F
Erica
UI
link landing page to login | bar: W6 10/10/2022 T to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
add profie link | bar: W6 10/10/2022 T to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
finalize navbar | bar: W6 10/10/2022 T to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
add shopping cart | bar: W6 10/10/2022 T to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
all links functioning | bar: W6 10/10/2022 T to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
make diagrams for UI Plan | bar: W11 11/14/2022 T to W11 11/14/2022 F
stylize forms | bar: W8 10/24/2022 W to W10 11/7/22 M; W11 11/14/2022 T to W11 11/14/2022 F
begin services | bar: W8 10/24/2022 W to W10 11/7/22 M; W11 11/14/2022 T to W11 11/14/2022 F
Complete Login Form UI | bar: W8 10/24/2022 W to W10 11/7/22 F; W11 11/14/2022 T to W11 11/14/2022 F
Style Equipment Rental UI | bar: W8 10/24/2022 W to W10 11/7/22 F; W11 11/14/2022 T to W11 11/14/2022 F
Complete Register Form UI | bar: W10 11/7/22 M to W10 11/7/22 F; W11 11/14/2022 T to W11 11/14/2022 F
Complete Shopping Cart Form UI | bar: W10 11/7/22 M to W10 11/7/22 F; W11 11/14/2022 T to W11 11/14/2022 F
UI for Class (Services) | bar: W10 11/7/22 M to W10 11/7/22 F; W11 11/14/2022 T to W12 11/21/2022 T
Style Admin Inventory Home | bar: W11 11/14/2022 T to W12 11/21/2022 F
Style Admin Inventory New | bar: W11 11/14/2022 T to W12 11/21/2022 F
Style Admin Inventory Update | bar: W11 11/14/2022 T to W12 11/21/2022 F
Style Equip Rental Employee | bar: W11 11/14/2022 T to W12 11/21/2022 F
Style User Account Page
UI for membership form | bar: W11 11/14/2022 T to W11 11/14/2022 F
Style Account Tab & Account Tab Edit | bar: W11 11/14/2022 T to W11 11/14/2022 F
Services
Create Class Schedle Layout | bar: W10 11/7/22 M to W10 11/7/22 F
Begin Class Schedule Backend | bar: W10 11/7/22 M to W10 11/7/22 F
Begin Backend for Memberships | bar: W10 11/7/22 M to W10 11/7/22 F; W11 11/14/2022 T to W11 11/14/2022 F
Beesanne
Inventory
Rental Checkout Customer Page to Display DB Info | bar: W6 10/10/2022 M to W7 10/17/2022 M; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
Rental Check-in Employee Portal | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
Admin Inventory Page | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
Product Tables with Data | bar: W6 10/10/2022 R to W7 10/17/2022 M; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
Upload to XAMMP | bar: W6 10/10/2022 R to W7 10/17/2022 M; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
Add Data for Products | bar: W6 10/10/2022 R to W7 10/17/2022 M; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
Work with Olamide to get Add to cart button functioning on Rental page | bar: W7 10/17/2022 W to W9 10/31/2022 M
Meet with Christina to Finalize Users Tables and upload to XAMMP | bar: W7 10/17/2022 W to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
Get photos to appear from DB | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
Upload Photos pack to XAMPP | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
Create Products Table | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
Add Data Validation to Admin Invetory | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
Get Admin Page Connected to DB | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
Begin Employee Rental Page | bar: W10 11/7/22 M to W10 11/7/22 F; W11 11/14/2022 T to W11 11/14/2022 F
Shopping Cart Table Functionality | bar: W11 11/14/2022 T to W11 11/14/2022 F; W12 11/21/2022 T to W12 11/21/2022 F
Database
Create Products Table | bar: W6 10/10/2022 T to W7 10/17/2022 M
Add Data to Unchanging Tables
Add User Tables | bar: W8 10/24/2022 M to W9 10/31/2022 M
Meet with Denizard to Discuss Tables in XAMPP
Olamide
working shopping cart class | bar: W5 10/6/2022 M to W7 10/17/2022 M; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
wokring DB | bar: W5 10/6/2022 M to W7 10/17/2022 M; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
Finish shopping cart form page | bar: W7 10/17/2022 W to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
work with Beesane to get Add to cart button functioning on retail page | bar: W7 10/17/2022 W to W9 10/31/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
shopping cart backend | bar: W7 10/17/2022 W to W10 11/7/22 M
Adjust Address Handling to match DB in CartAction | bar: W8 10/24/2022 M to W8 10/24/2022 F; W10 11/7/22 M to W11 11/14/2022 F
Run Test Cases on Shopping Cart | bar: W8 10/24/2022 M to W8 10/24/2022 F; W10 11/7/22 M to W12 11/21/2022 M
Complete Shopping Cart Form Integration | bar: W8 10/24/2022 M to W8 10/24/2022 F; W10 11/7/22 M to W11 11/14/2022 F
Make Shopping Cart Dynamic | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W12 11/21/2022 F
Complete Shopping Cart Checkout | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W12 11/21/2022 F
4 | Meetings
4.1 | Webex Group Week 1 | All | N/A | N/A | #VALUE! | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
4.2 | Webex Group Week 2 | All | N/A | N/A | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
4.2.1 | Webex Group Week 3 | All | 2022-09-19 | 2022-09-19 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
9/ | Webex Denizard: UI / General | Erica, All Optional | 2022-09-25 | 2022-09-25 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
4.3.2 | Webex Group Week 4 | All | 2022-09-26 | 2022-09-26 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
4.3.3 | Webex Group Week 5 | All | 2022-10-03 | 2022-10-03 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
| Webex Group Week 6 | All | 2022-10-10 | 2022-10-10 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
4.3.3 | In-Person Group Week 6 | All | 2022-10-10 | 2022-10-10 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F