## Gantt Chart
GANTT CHART
PROJECT TITLE |  | POS - Power House Phitness (PHP) |  |  |  |  | ORGANIZATION NAME | [6 empty] | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE | [6 empty] | 2022-10-24
GROUP LEADER |  | Charles Olinsky
GROUP MEMBERS |  | Erica Dubie, Beesanne Kurzum, Olamide Kumapayi, Christina Rodriguez
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 9/8/2022 |  |  |  |  | W2 9/15/2022 |  |  |  |  | W3 9/22/2022 |  |  |  |  | W4 9/29/2022 |  |  |  |  | W5 10/6/2022 |  |  |  |  | W6 10/10/2022 |  |  |  |  | W7 10/17/2022 |  |  |  |  | W8 10/24/2022 |  |  |  |  | W9 10/31/2022 |  |  |  |  | W10 11/7/22 |  |  |  |  | W11 11/14/2022 |  |  |  |  | W12 11/21/2022 |  |  |  |  | W13 11/28/2022 |  |  |  |  | W14 12/5/2022
1 | Proct Conception and Initiation | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1.1 | Setting up Github | All | 2022-09-05 | 2022-09-05 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F
1.1.1 | Setting up Discord | All | 2022-09-05 | 2022-09-05 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F
1.2 | Setting up XAMPP | All | 2022-09-06 | 2022-09-08 | 2 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F
1.3 | Assigning Group Leader | All | 2022-09-06 | 2022-09-06 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F
1.4 | Deciding on a Concept | All | 2022-09-05 | 2022-09-05 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F
1.5 | Create Directory Structure | Charlie | 2022-09-20 | 2022-09-20 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F
1.6 | Clarify Concept - Fitness Center | All | 2022-09-26 | 2022-09-26 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F
1.7 | Decide on Project Name | All | 2022-09-26 | 2022-09-26 | 0 | 100% | bar: W8 10/24/2022 M to W8 10/24/2022 F
| FINAL PRESENTATION SCRIPTS | All | 2022-11-21 | 2022-11-26 | 5 | bar: W8 10/24/2022 M to W8 10/24/2022 F
Powerpoint | bar: W8 10/24/2022 M to W8 10/24/2022 F
2 | Planning
2.1 | Users - 3 classes | Christina |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F
2.2 | Financial Reports - Z Reports - CashFlow | Christina |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F
2.3 | Inventory - Details - Vendor - TTL | Beesanne |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F
2.3.1 | Services | Erica, Charlie |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F
2.4 | Shopping Cart - Payment | Olamide, Beesanne |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F
2.5 | Reciepts | Olamide |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F
2.6 | Security | Charlie |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F
2.7 | Sessions Class | Charlie |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F
2.8 | Data Management | Beesanne |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F
2.9 | UI | Erica |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F
2.1 | Email Notifications | Charlie |  |  | 0 | 0% | bar: W8 10/24/2022 M to W8 10/24/2022 F
| Presentation Narration | Erica | bar: W8 10/24/2022 M to W8 10/24/2022 F
2.11 | bar: W8 10/24/2022 M to W8 10/24/2022 F
3 | Coding and Assembly
Charlie
Sessions Class
Intialize the Sessions class | bar: W6 10/10/2022 W to W7 10/17/2022 M
Meet with Denizard to discuss implementation | bar: W8 10/24/2022 R
Begin using HTTP Only Cookies in sessions | bar: W7 10/17/2022 W to W8 10/24/2022 M
Integrate Sessions into User Class | bar: W7 10/17/2022 W to W10 11/7/22 F
Integrate Sessions into Shopping Cart Class | bar: W8 10/24/2022 W to W11 11/14/2022 F
Add Timeout method to the sessions class | bar: W9 10/31/2022 M to W10 11/7/22 M
Add Error Handling method to the sessions class | bar: W9 10/31/2022 M to W10 11/7/22 M
Integrate Sessions Class into User Class pt2
New sessions into account tab
Logout Function (in user profile)
Integrate Sessions Class across all Classes and Forms
Use Cookies to Carry Cart Data between Sessions
Security
Begin Encrypting Data | bar: W6 10/10/2022 W to W7 10/17/2022 M
Create password hashing function | bar: W7 10/17/2022 W to W8 10/24/2022 M
Integrate Security and User Classes | bar: W9 10/31/2022 M to W10 11/7/22 F
Ensure safe queries | bar: W9 10/31/2022 M to W10 11/7/22 F
Protect against IP Spoofing | bar: W9 10/31/2022 M to W10 11/7/22 M
Implement Proper CSRF Protection | bar: W9 10/31/2022 M to W10 11/7/22 T; W12 11/21/2022 T to W12 11/21/2022 W
Services
Complete Membership Backend | bar: W12 11/21/2022 W to W12 11/21/2022 F
Begin Classes Backend | bar: W12 11/21/2022 W to W12 11/21/2022 F
Create Dynamic Class Cards | bar: W12 11/21/2022 W to W12 11/21/2022 F
Add Sign-up Button Handeler to Classes | bar: W12 11/21/2022 W to W12 11/21/2022 F
MISC
Link account_tab to loginUI
Link register.php to loginUI
Create Admin Portal
Christina
User Classes
Create Test Table PHPmyAdminj | bar: W6 10/10/2022 W to W7 10/17/2022 M
Implement SQL Queries in User Class Functions | bar: W6 10/10/2022 W to W7 10/17/2022 M
Test Creation of all 5 users | bar: W6 10/10/2022 W to W7 10/17/2022 M
error handeling
connect to login
roles class with access levels | bar: W8 10/24/2022 M to W9 10/31/2022 M
php code for calculations
User Class Method Functionality | bar: W8 10/24/2022 W to W9 10/31/2022 W
Finish createUser() function | bar: W10 11/7/22 M to W11 11/14/2022 F
Add editUser() function | bar: W10 11/7/22 M to W11 11/14/2022 F
Add deleteUser() Function | bar: W10 11/7/22 M to W11 11/14/2022 F
Create Admin Page | bar: W11 11/14/2022 T to W12 11/21/2022 T
User page search error
Flowchart
Financial Reports
Different Report Types
Service Reports
Reports Tables
Create Test Data | bar: W11 11/14/2022 T to W12 11/21/2022 F
Test Reporting Functions | bar: W11 11/14/2022 T to W12 11/21/2022 F
Generate Z-Report PDF | bar: W11 11/14/2022 T to W12 11/21/2022 F
Z-Report Searchable by Date
Erica
UI
link landing page to login | bar: W6 10/10/2022 T to W7 10/17/2022 M
add profie link | bar: W6 10/10/2022 T to W7 10/17/2022 M
finalize navbar | bar: W6 10/10/2022 T to W7 10/17/2022 M
add shopping cart | bar: W6 10/10/2022 T to W7 10/17/2022 M
all links functioning | bar: W6 10/10/2022 T to W7 10/17/2022 M
make diagrams for UI Plan
stylize forms | bar: W8 10/24/2022 W to W10 11/7/22 M
begin services | bar: W8 10/24/2022 W to W10 11/7/22 M
Complete Login Form UI | bar: W8 10/24/2022 W to W10 11/7/22 F
Style Equipment Rental UI | bar: W8 10/24/2022 W to W10 11/7/22 F
Complete Register Form UI | bar: W10 11/7/22 M to W11 11/14/2022 F
Complete Shopping Cart Form UI | bar: W10 11/7/22 M to W10 11/7/22 F
UI for Class (Services) | bar: W10 11/7/22 M to W10 11/7/22 F; W11 11/14/2022 T to W12 11/21/2022 T
Style Admin Inventory Home | bar: W11 11/14/2022 T to W12 11/21/2022 F
Style Admin Inventory New | bar: W12 11/21/2022 T to W12 11/21/2022 F
Style Admin Inventory Update | bar: W12 11/21/2022 T to W12 11/21/2022 F
Style Equip Rental Employee | bar: W12 11/21/2022 T to W12 11/21/2022 F
Style User Account Page | bar: W11 11/14/2022 T to W12 11/21/2022 F
UI for membership form | bar: W12 11/21/2022 F
Style Account Tab & Account Tab Edit | bar: W12 11/21/2022 F
LoginUI fix
Shopping Cart UI
Checkout UI
Update aboutUs
Membersuccess form
admin portal forms
update navbars
Services
Create Class Schedle Layout | bar: W10 11/7/22 M to W10 11/7/22 F
Begin Class Schedule Backend | bar: W10 11/7/22 M to W10 11/7/22 F
Begin Backend for Memberships | bar: W10 11/7/22 M to W11 11/14/2022 F
Classes UI | bar: W10 11/7/22 M to W12 11/21/2022 F
Beesanne
Inventory
Rental Checkout Customer Page to Display DB Info | bar: W6 10/10/2022 M to W7 10/17/2022 M
Rental Check-in Employee Portal
Admin Inventory Page | bar: W8 10/24/2022 W to W8 10/24/2022 F
Product Tables with Data | bar: W6 10/10/2022 R to W7 10/17/2022 M
Upload to XAMMP | bar: W6 10/10/2022 R to W7 10/17/2022 M
Add Data for Products | bar: W6 10/10/2022 R to W7 10/17/2022 M
Work with Olamide to get Add to cart button functioning on Rental page | bar: W7 10/17/2022 W to W9 10/31/2022 M
Meet with Christina to Finalize Users Tables and upload to XAMMP | bar: W7 10/17/2022 W to W8 10/24/2022 M
Get photos to appear from DB | bar: W8 10/24/2022 M
Upload Photos pack to XAMPP | bar: W8 10/24/2022 M to W8 10/24/2022 F
Create Products Table | bar: W8 10/24/2022 M to W8 10/24/2022 F
Add Data Validation to Admin Invetory | bar: W8 10/24/2022 M to W8 10/24/2022 F
Get Admin Page Connected to DB | bar: W8 10/24/2022 M to W8 10/24/2022 F
Begin Employee Rental Page | bar: W10 11/7/22 M to W11 11/14/2022 F
Shopping Cart Table Functionality | bar: W12 11/21/2022 T to W12 11/21/2022 F
Vendor name admin page
presentation work (commenting, diagrams)
Database
Create Products Table | bar: W6 10/10/2022 T to W7 10/17/2022 M
Add Data to Unchanging Tables
Add User Tables | bar: W8 10/24/2022 M to W9 10/31/2022 M
Meet with Denizard to Discuss Tables in XAMPP
Finalize Schema
Olamide
Shopping Cart & Recipts
working shopping cart class | bar: W5 10/6/2022 M to W7 10/17/2022 M; W8 10/24/2022 M to W8 10/24/2022 F
wokring DB | bar: W5 10/6/2022 M to W7 10/17/2022 M; W8 10/24/2022 M to W8 10/24/2022 F
Finish shopping cart form page | bar: W7 10/17/2022 W to W8 10/24/2022 F
work with Beesane to get Add to cart button functioning on retail page | bar: W7 10/17/2022 W to W9 10/31/2022 M
shopping cart backend | bar: W7 10/17/2022 W to W10 11/7/22 M; W11 11/14/2022 T to W12 11/21/2022 M
Adjust Address Handling to match DB in CartAction | bar: W8 10/24/2022 M to W8 10/24/2022 F; W10 11/7/22 M to W11 11/14/2022 F
Run Test Cases on Shopping Cart | bar: W8 10/24/2022 M to W8 10/24/2022 F; W10 11/7/22 M to W12 11/21/2022 M
Complete Shopping Cart Form Integration | bar: W8 10/24/2022 M to W8 10/24/2022 F; W10 11/7/22 M to W11 11/14/2022 F
Make Shopping Cart Dynamic | bar: W8 10/24/2022 M to W8 10/24/2022 F; W12 11/21/2022 T to W12 11/21/2022 F
Complete Shopping Cart Checkout | bar: W8 10/24/2022 M to W8 10/24/2022 F; W12 11/21/2022 T to W12 11/21/2022 F
Complete Checkout | bar: W8 10/24/2022 M to W8 10/24/2022 F
Presentation work