## Gantt Chart
GANTT CHART
PROJECT TITLE |  | POS - Power House Phitness (PHP) |  |  |  |  | ORGANIZATION NAME | [6 empty] | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE | [6 empty] | 2022-12-07
GROUP LEADER |  | Charles Olinsky
GROUP MEMBERS |  | Erica Dubie, Beesanne Kurzum, Olamide Kumapayi, Christina Rodriguez
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 9/5/2022 |  |  |  |  | W2 9/12/2022 |  |  |  |  | W3 9/19/2022 |  |  |  |  | W4 9/26/2022 |  |  |  |  | W5 10/3/2022 |  |  |  |  | W6 10/10/2022 |  |  |  |  | W7 10/17/2022 |  |  |  |  | W8 10/24/2022 |  |  |  |  | W9 10/31/2022 |  |  |  |  | W10 11/7/22 |  |  |  |  | W11 11/14/2022 |  |  |  |  | W12 11/21/2022 |  |  |  |  | W13 11/28/2022 |  |  |  |  | W14 12/5/2022
1 | Proct Conception and Initiation | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R
1.1 | Setting up Github | All | 2022-09-05 | 2022-09-05 | 0 | 100% | bar: W1 9/5/2022 M; W2 9/12/2022 M to W2 9/12/2022 F; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
1.1.1 | Setting up Discord | All | 2022-09-05 | 2022-09-05 | 0 | 100% | bar: W1 9/5/2022 M; W2 9/12/2022 M to W2 9/12/2022 F; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
1.2 | Setting up XAMPP | All | 2022-09-06 | 2022-09-08 | 2 | 100% | bar: W1 9/5/2022 T to W2 9/12/2022 F; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
1.3 | Assigning Group Leader | All | 2022-09-06 | 2022-09-06 | 0 | 100% | bar: W1 9/5/2022 M to W1 9/5/2022 T; W2 9/12/2022 M to W2 9/12/2022 F; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
1.4 | Deciding on a Concept | All | 2022-09-05 | 2022-09-05 | 0 | 100% | bar: W1 9/5/2022 M; W2 9/12/2022 M to W2 9/12/2022 F; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
1.5 | Create Directory Structure | Charlie | 2022-09-20 | 2022-09-20 | 0 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W3 9/19/2022 T; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
1.6 | Clarify Concept - Fitness Center | All | 2022-09-26 | 2022-09-26 | 0 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W4 9/26/2022 M; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
1.7 | Decide on Project Name | All | 2022-09-26 | 2022-09-26 | 0 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W4 9/26/2022 M; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2 | Planning
2.1 | Users - 3 classes | Christina | 2022-09-19 | 2022-09-19 | 0 | 100% | bar: W2 9/12/2022 M to W3 9/19/2022 M; W4 9/26/2022 T to W6 10/10/2022 T; W6 10/10/2022 R to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.2 | Financial Reports - Z Reports - CashFlow | Christina | 2022-09-19 | 2022-09-19 | 0 | 100% | bar: W2 9/12/2022 M to W3 9/19/2022 M; W5 10/3/2022 M to W5 10/3/2022 F; W6 10/10/2022 R to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.3 | Inventory - Details - Vendor - TTL | Beesanne | 2022-09-19 | 2022-09-19 | 0 | 100% | bar: W2 9/12/2022 M to W3 9/19/2022 M; W5 10/3/2022 M to W5 10/3/2022 F; W6 10/10/2022 R to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.3.1 | Services | Erica, Charlie | 2022-09-19 | 2022-09-19 | 0 | 100% | bar: W2 9/12/2022 M to W3 9/19/2022 M; W5 10/3/2022 M to W5 10/3/2022 F; W6 10/10/2022 R to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.4 | Shopping Cart - Payment | Olamide, Beesanne | 2022-09-19 | 2022-09-19 | 0 | 100% | bar: W2 9/12/2022 M to W3 9/19/2022 M; W5 10/3/2022 M to W5 10/3/2022 F; W6 10/10/2022 R to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.5 | Reciepts | Olamide | 2022-09-19 | 2022-09-19 | 0 | 100% | bar: W2 9/12/2022 M to W3 9/19/2022 M; W5 10/3/2022 M to W5 10/3/2022 F; W6 10/10/2022 R to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.6 | Security | Charlie | 2022-09-19 | 2022-09-19 | 0 | 100% | bar: W2 9/12/2022 M to W3 9/19/2022 M; W5 10/3/2022 M to W5 10/3/2022 F; W6 10/10/2022 R to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.7 | Sessions Class | Charlie | 2022-09-19 | 2022-09-19 | 0 | 100% | bar: W2 9/12/2022 M to W3 9/19/2022 M; W5 10/3/2022 M to W5 10/3/2022 F; W6 10/10/2022 R to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.8 | Data Management | Beesanne | 2022-09-19 | 2022-09-19 | 0 | 100% | bar: W2 9/12/2022 M to W3 9/19/2022 M; W5 10/3/2022 M to W5 10/3/2022 F; W6 10/10/2022 R to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.9 | UI | Erica | 2022-09-19 | 2022-09-19 | 0 | 100% | bar: W2 9/12/2022 M to W3 9/19/2022 M; W5 10/3/2022 M to W5 10/3/2022 F; W6 10/10/2022 R to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.1 | Email Notifications | Charlie | 2022-09-19 | 2022-09-19 | 0 | 100% | bar: W2 9/12/2022 M to W3 9/19/2022 M; W5 10/3/2022 M to W5 10/3/2022 F; W6 10/10/2022 R to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
2.11 | FINAL PRESENTATION SCRIPTS | All | 2022-11-21 | 2022-11-22 | 1 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W6 10/10/2022 R to W8 10/24/2022 F; W11 11/14/2022 T to W12 11/21/2022 W
2.12 | Powerpoint | All | 2022-12-01 | 2022-12-07 | 6 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W6 10/10/2022 R to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W13 11/28/2022 T to W14 12/5/2022 W
2.13 | Presentation Narration | Erica | 2022-12-01 | 2022-12-07 | 6 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W6 10/10/2022 R to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W13 11/28/2022 T to W14 12/5/2022 W
3 | Coding and Assembly
Charlie
Sessions Class
3.1 | Intialize the Sessions class | Charlie | 2022-10-12 | 2022-10-17 | 5 | 100% | bar: W6 10/10/2022 W to W7 10/17/2022 M
3.2 | Meet with Denizard to discuss implementation | Charlie | 2022-10-27 | 2022-10-27 | 0 | 100% | bar: W8 10/24/2022 R
3.3 | Begin using HTTP Only Cookies in sessions | Charlie | 2022-10-19 | 2022-10-24 | 5 | 100% | bar: W7 10/17/2022 W to W8 10/24/2022 M
3.4 | Integrate Sessions into User Class | Charlie | 2022-10-19 | 2022-11-11 | 22 | 100% | bar: W7 10/17/2022 W to W10 11/7/22 F
3.5 | Integrate Sessions into Shopping Cart Class | Charlie | 2022-10-26 | 2022-11-18 | 22 | 100% | bar: W8 10/24/2022 R to W11 11/14/2022 F
3.6 | Add Timeout method to the sessions class | Charlie | 2022-10-31 | 2022-11-07 | 7 | 100% | bar: W9 10/31/2022 M to W10 11/7/22 M
3.7 | Add Error Handling method to the sessions class | Charlie | 2022-10-31 | 2022-11-07 | 7 | 100% | bar: W9 10/31/2022 M to W10 11/7/22 M
3.8 | Integrate Sessions Class into User Class pt2 | Charlie | 2022-11-15 | 2022-11-18 | 3 | 100% | bar: W11 11/14/2022 T to W11 11/14/2022 F
3.9 | New sessions into account tab | Charlie | 2022-11-19 | 2022-11-22 | 3 | 100% | bar: W11 11/14/2022 F to W12 11/21/2022 R
3.10 | Logout Function (in user profile) | Charlie | 2022-11-19 | 2022-11-22 | 3 | 100%
3.11 | Integrate Sessions Class across all Classes and Forms | Charlie | 2022-11-22 | 2022-11-30 | 8 | 100%
3.12 | Use Cookies to Carry Cart Data between Sessions | Charlie | 2022-11-26 | 2022-11-30 | 4 | 100%
Security
3.13 | Begin Encrypting Data | Charlie | 2022-10-12 | 2022-10-17 | 5 | 100% | bar: W6 10/10/2022 W to W7 10/17/2022 M
3.14 | Create password hashing function | Charlie | 2022-10-19 | 2022-10-24 | 5 | 100% | bar: W7 10/17/2022 W to W8 10/24/2022 M
3.15 | Integrate Security and User Classes | Charlie | 2022-10-31 | 2022-11-11 | 11 | 100% | bar: W9 10/31/2022 M to W10 11/7/22 F
3.16 | Ensure safe queries | Charlie | 2022-10-31 | 2022-11-11 | 11 | 100% | bar: W9 10/31/2022 M to W10 11/7/22 F
3.17 | Protect against IP Spoofing | Charlie | 2022-10-31 | 2022-11-07 | 7 | 100% | bar: W9 10/31/2022 M to W10 11/7/22 M; W11 11/14/2022 T to W11 11/14/2022 F
3.18 | Implement Proper CSRF Protection | Charlie | 2022-10-31 | 2022-11-08 | 8 | 100% | bar: W9 10/31/2022 M to W10 11/7/22 T; W12 11/21/2022 T to W12 11/21/2022 W
Services
3.19 | Complete Membership Backend | Charlie | 2022-11-23 | 2022-11-28 | 5 | 100% | bar: W12 11/21/2022 W to W12 11/21/2022 F
3.2 | Begin Classes Backend | Charlie | 2022-11-23 | 2022-11-28 | 5 | 100% | bar: W12 11/21/2022 W to W12 11/21/2022 F
3.21 | Create Dynamic Class Cards | Charlie | 2022-11-23 | 2022-11-28 | 5 | 100% | bar: W12 11/21/2022 W to W12 11/21/2022 F
3.22 | Add Sign-up Button Handeler to Classes | Charlie | 2022-11-23 | 2022-11-28 | 5 | 100% | bar: W12 11/21/2022 W to W12 11/21/2022 F
MISC
3.23 | Link account_tab to loginUI | Charlie | 2022-11-29 | 2022-11-29 | 0 | 100% | bar: W13 11/28/2022 M
3.24 | Link register.php to loginUI | Charlie | 2022-11-29 | 2022-11-29 | 0 | 100% | bar: W13 11/28/2022 M
3.25 | Create Admin Portal | Charlie | 2022-11-29 | 2022-11-29 | 0 | 100% | bar: W13 11/28/2022 M
Christina
User Classes
3.26 | Create Test Table PHPmyAdminj | Christina | 2022-10-13 | 2022-10-17 | 4 | 100% | bar: W6 10/10/2022 W to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.27 | Implement SQL Queries in User Class Functions | Christina | 2022-10-13 | 2022-10-17 | 4 | 100% | bar: W6 10/10/2022 W to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.28 | Test Creation of all 5 users | Christina | 2022-10-13 | 2022-10-17 | 4 | 100% | bar: W6 10/10/2022 W to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.29 | error handeling | Christina | 2022-10-17 | 2022-10-22 | 5 | 100% | bar: W7 10/17/2022 M to W7 10/17/2022 R; W11 11/14/2022 T to W11 11/14/2022 F
3.3 | connect to login | Christina | 2022-10-17 | 2022-10-23 | 6 | 100% | bar: W7 10/17/2022 M to W7 10/17/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
3.31 | roles class with access levels | Christina | 2022-10-24 | 2022-11-02 | 8 | 100% | bar: W8 10/24/2022 M to W9 10/31/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.32 | php code for calculations | Christina | 2022-10-26 | 2022-11-04 | 8 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W8 10/24/2022 W to W9 10/31/2022 W; W11 11/14/2022 T to W11 11/14/2022 F
3.33 | User Class Method Functionality | Christina | 2022-11-07 | 2022-11-14 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W8 10/24/2022 W to W9 10/31/2022 W; W11 11/14/2022 T to W11 11/14/2022 F
3.34 | Finish createUser() function | Christina | 2022-11-07 | 2022-11-14 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W10 11/7/22 M to W11 11/14/2022 F
3.35 | Add editUser() function | Christina | 2022-11-07 | 2022-11-14 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W10 11/7/22 M to W11 11/14/2022 F
3.36 | Add deleteUser() Function | Christina | 2022-11-15 | 2022-11-22 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W10 11/7/22 M to W11 11/14/2022 F
3.37 | Create Admin Page | Christina | 2022-11-14 | 2022-11-22 | 8 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W12 11/21/2022 T
3.38 | User page search error | Christina | 2022-11-22 | 2022-11-25 | 3 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W12 11/21/2022 T to W12 11/21/2022 R
3.39 | Flowchart | Christina | 2022-12-01 | 2022-12-06 | 5 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W13 11/28/2022 R to W14 12/5/2022 W
Financial Reports
3.40 | Different Report Types | Christina | 2022-11-21 | 2022-11-28 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W12 11/21/2022 M to W12 11/21/2022 F
3.41 | Service Reports | Christina | 2022-11-21 | 2022-11-28 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W12 11/21/2022 M to W12 11/21/2022 F
3.42 | Reports Tables | Christina | 2022-11-18 | 2022-11-28 | 10 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 R to W12 11/21/2022 F
3.43 | Create Test Data | Christina | 2022-11-18 | 2022-11-28 | 10 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W12 11/21/2022 F
3.44 | Test Reporting Functions | Christina | 2022-11-15 | 2022-11-28 | 13 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W12 11/21/2022 F
3.45 | Generate Z-Report PDF | Christina | 2022-11-15 | 2022-11-28 | 13 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W12 11/21/2022 F
Erica
UI
3.46 | link landing page to login | Erica | 2022-10-10 | 2022-10-17 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W6 10/10/2022 T to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.47 | add profie link | Erica | 2022-10-10 | 2022-10-17 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W6 10/10/2022 T to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.48 | finalize navbar | Erica | 2022-10-10 | 2022-10-17 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W6 10/10/2022 T to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.49 | add shopping cart | Erica | 2022-10-10 | 2022-10-17 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W6 10/10/2022 T to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.5 | all links functioning | Erica | 2022-10-10 | 2022-10-17 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W6 10/10/2022 T to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.51 | make diagrams for UI Plan | Erica | 2022-10-20 | 2022-10-26 | 6 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W7 10/17/2022 R to W8 10/24/2022 W; W11 11/14/2022 T to W11 11/14/2022 F
3.52 | stylize forms | Erica | 2022-10-26 | 2022-11-07 | 11 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W8 10/24/2022 W to W10 11/7/22 M; W11 11/14/2022 T to W11 11/14/2022 F
3.53 | begin services | Erica | 2022-10-26 | 2022-11-07 | 11 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W8 10/24/2022 W to W10 11/7/22 M; W11 11/14/2022 T to W11 11/14/2022 F
3.54 | Complete Login Form UI | Erica | 2022-10-26 | 2022-11-14 | 18 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W8 10/24/2022 W to W10 11/7/22 F; W11 11/14/2022 T to W11 11/14/2022 F
3.55 | Style Equipment Rental UI | Erica | 2022-10-26 | 2022-11-14 | 18 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W8 10/24/2022 W to W10 11/7/22 F; W11 11/14/2022 T to W11 11/14/2022 F
3.56 | Complete Register Form UI | Erica | 2022-11-07 | 2022-11-16 | 9 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W10 11/7/22 M to W11 11/14/2022 F
3.57 | Complete Shopping Cart Form UI | Erica | 2022-11-07 | 2022-11-11 | 4 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W10 11/7/22 M to W10 11/7/22 F; W11 11/14/2022 T to W11 11/14/2022 F
3.58 | UI for Class (Services) | Erica | 2022-11-07 | 2022-11-21 | 14 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W10 11/7/22 M to W12 11/21/2022 T
3.59 | Style Admin Inventory Home | Erica | 2022-11-21 | 2022-11-24 | 3 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W12 11/21/2022 F
3.6 | Style Admin Inventory New | Erica | 2022-11-22 | 2022-11-24 | 2 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W12 11/21/2022 T to W12 11/21/2022 F
3.61 | Style Admin Inventory Update | Erica | 2022-11-22 | 2022-11-24 | 2 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W12 11/21/2022 T to W12 11/21/2022 F
3.62 | Style Equip Rental Employee | Erica | 2022-11-22 | 2022-11-25 | 3 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W12 11/21/2022 T to W12 11/21/2022 F
3.63 | Style User Account Page | Erica | 2022-11-15 | 2022-11-25 | 10 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W12 11/21/2022 F
3.64 | UI for membership form | Erica | 2022-11-25 | 2022-11-25 | 0 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W12 11/21/2022 F
3.65 | Style Account Tab & Account Tab Edit | Erica | 2022-11-25 | 2022-11-25 | 0 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W12 11/21/2022 F
3.66 | LoginUI fix | Erica | 2022-11-23 | 2022-11-25 | 2 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W12 11/21/2022 W to W13 11/28/2022 M
3.67 | Shopping Cart UI | Erica | 2022-11-25 | 2022-11-27 | 2 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W12 11/21/2022 F to W13 11/28/2022 T
3.68 | Checkout UI | Erica | 2022-11-25 | 2022-11-27 | 2 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W12 11/21/2022 F to W13 11/28/2022 T
3.69 | Update aboutUs | Erica | 2022-11-25 | 2022-11-27 | 2 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W12 11/21/2022 F to W13 11/28/2022 T
3.7 | Membersuccess form | Erica | 2022-11-26 | 2022-12-01 | 5 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W13 11/28/2022 M to W13 11/28/2022 R
3.71 | admin portal forms | Erica | 2022-11-26 | 2022-12-01 | 5 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W13 11/28/2022 M to W13 11/28/2022 R
3.72 | update navbars | Erica | 2022-11-30 | 2022-12-01 | 1 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W13 11/28/2022 W to W13 11/28/2022 R
Services
3.73 | Create Class Schedle Layout | Erica | 2022-11-07 | 2022-11-11 | 4 | 100% | bar: W10 11/7/22 M to W10 11/7/22 F
3.74 | Begin Class Schedule Backend | Erica | 2022-11-07 | 2022-11-11 | 4 | 100% | bar: W10 11/7/22 M to W10 11/7/22 F
3.75 | Begin Backend for Memberships | Erica | 2022-11-07 | 2022-11-19 | 12 | 100% | bar: W10 11/7/22 M to W11 11/14/2022 F
3.76 | Classes UI | Erica | 2022-11-07 | 2022-11-25 | 18 | 100% | bar: W10 11/7/22 M to W12 11/21/2022 F
Beesanne
Inventory
3.77 | Rental Checkout Customer Page to Display DB Info | Beesanne | 2022-10-10 | 2022-10-17 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W6 10/10/2022 M to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.78 | Rental Check-in Employee Portal | Beesanne | 2022-10-10 | 2022-10-17 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W6 10/10/2022 M to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.79 | Admin Inventory Page | Beesanne | 2022-10-25 | 2022-10-27 | 2 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W8 10/24/2022 W to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
3.8 | Product Tables with Data | Beesanne | 2022-10-14 | 2022-10-17 | 3 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W6 10/10/2022 R to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.81 | Upload to XAMMP | Beesanne | 2022-10-14 | 2022-10-17 | 3 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W6 10/10/2022 R to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.82 | Add Data for Products | Beesanne | 2022-10-14 | 2022-10-17 | 3 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W6 10/10/2022 R to W7 10/17/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.83 | Work with Olamide to get Add to cart button functioning on Rental page | Beesanne | 2022-10-18 | 2022-11-23 | 35 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W7 10/17/2022 W to W12 11/21/2022 R
3.84 | Meet with Christina to Finalize Users Tables and upload to XAMMP | Beesanne | 2022-10-18 | 2022-10-24 | 6 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W7 10/17/2022 W to W8 10/24/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.85 | Get photos to appear from DB | Beesanne | 2022-10-24 | 2022-10-24 | 0 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W8 10/24/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.86 | Upload Photos pack to XAMPP | Beesanne | 2022-10-24 | 2022-10-28 | 4 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
3.87 | Create Products Table | Beesanne | 2022-10-24 | 2022-10-28 | 4 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
3.88 | Add Data Validation to Admin Invetory | Beesanne | 2022-10-24 | 2022-10-28 | 4 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
3.89 | Get Admin Page Connected to DB | Beesanne | 2022-10-24 | 2022-10-28 | 4 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
3.9 | Begin Employee Rental Page | Beesanne | 2022-11-07 | 2022-11-14 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W10 11/7/22 M to W11 11/14/2022 F
3.91 | Shopping Cart Table Functionality | Beesanne | 2022-11-21 | 2022-11-25 | 4 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W12 11/21/2022 T to W12 11/21/2022 F
3.92 | Vendor name admin page | Beesanne | 2022-11-28 | 2022-11-30 | 2 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W13 11/28/2022 M to W13 11/28/2022 W
3.93 | presentation work (commenting, diagrams) | Beesanne | 2022-12-01 | 2022-12-07 | 6 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W13 11/28/2022 R to W14 12/5/2022 W
Database
3.94 | Create Products Table | Beesanne | 2022-10-12 | 2022-10-17 | 5 | 100% | bar: W6 10/10/2022 T to W7 10/17/2022 M
3.95 | Add Data to Unchanging Tables | Beesanne | 2022-10-12 | 2022-10-20 | 8 | 100% | bar: W6 10/10/2022 F to W7 10/17/2022 R
3.96 | Add User Tables | Beesanne | 2022-10-21 | 2022-10-31 | 10 | 100% | bar: W7 10/17/2022 F to W9 10/31/2022 M
3.97 | Meet with Denizard to Discuss Tables in XAMPP | Beesanne | 2022-11-10 | 2022-11-10 | 0 | 100% | bar: W10 11/7/22 R
3.98 | Finalize Schema | Beesanne | 2022-11-25 | 2022-12-05 | 10 | 100% | bar: W12 11/21/2022 F to W14 12/5/2022 M
Olamide
Shopping Cart & Recipts
3.99 | working shopping cart class | Olamide | 2022-10-10 | 2022-10-17 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W7 10/17/2022 M; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
3.1 | wokring DB | Olamide | 2022-10-10 | 2022-10-17 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W7 10/17/2022 M; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
3.101 | Finish shopping cart form page | Olamide | 2022-10-19 | 2022-10-24 | 5 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W7 10/17/2022 W to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F
3.102 | work with Beesane to get Add to cart button functioning on retail page | Olamide | 2022-10-19 | 2022-10-31 | 12 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W7 10/17/2022 W to W9 10/31/2022 M; W11 11/14/2022 T to W11 11/14/2022 F
3.103 | shopping cart backend | Olamide | 2022-10-19 | 2022-11-21 | 32 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W7 10/17/2022 W to W12 11/21/2022 M
3.104 | Adjust Address Handling to match DB in CartAction | Olamide | 2022-11-07 | 2022-11-14 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W8 10/24/2022 M to W8 10/24/2022 F; W10 11/7/22 M to W11 11/14/2022 F
3.105 | Run Test Cases on Shopping Cart | Olamide | 2022-11-07 | 2022-11-21 | 14 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W8 10/24/2022 M to W8 10/24/2022 F; W10 11/7/22 M to W12 11/21/2022 M
3.106 | Complete Shopping Cart Form Integration | Olamide | 2022-11-07 | 2022-11-14 | 7 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W8 10/24/2022 M to W8 10/24/2022 F; W10 11/7/22 M to W11 11/14/2022 F
3.107 | Make Shopping Cart Dynamic | Olamide | 2022-11-21 | 2022-11-25 | 4 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W12 11/21/2022 T to W12 11/21/2022 F
3.108 | Complete Shopping Cart Checkout | Olamide | 2022-11-21 | 2022-11-25 | 4 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W12 11/21/2022 T to W12 11/21/2022 F
3.109 | Complete Checkout | Olamide | 2022-11-25 | 2022-11-28 | 3 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W5 10/3/2022 M to W5 10/3/2022 F; W8 10/24/2022 M to W8 10/24/2022 F; W11 11/14/2022 T to W11 11/14/2022 F; W12 11/21/2022 F to W13 11/28/2022 T
3.11 | Presentation work | Olamide | 2022-12-01 | 2022-12-05 | 4 | 100% | bar: W2 9/12/2022 M to W2 9/12/2022 F; W13 11/28/2022 R to W14 12/5/2022 W