## Gantt Chart
GANTT CHART
PROJECT TITLE |  | POS - Power House Phitness (PHP) |  |  |  |  | ORGANIZATION NAME |  | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE |  | 2022-10-03
GROUP LEADER |  | Charles Olinsky
GROUP MEMBERS |  | Erica Dubie, Beesanne Kurzum, Olamide Kumapayi, Christina Rodriguez
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 9/8/2021 | W2 9/15/2021 |  | W3 9/22/2021 | W4 9/29/2021 | W5 10/6/2021 | W6 10/13/2021 | W7 10/20/2021 | W8 10/27/2021 | W9 11/3/2021 | W10 11/10/2021 | W11 11/17/2021 | W12 11/24/2021 | W13 12/1/2021 | W14 12/8/2021
1 | Proct Conception and Initiation
1.1 | Setting up Github | All | 2022-09-05 | 2022-09-05 | 0 | 100%
1.1.1 | Setting up Discord | All | 2022-09-05 | 2022-09-05 | 0 | 100%
1.2 | Setting up XAMPP | All | 2022-09-06 | 2022-09-08 | 2 | 100%
1.3 | Assigning Group Leader | All | 2022-09-06 | 2022-09-06 | 0 | 100%
1.4 | Deciding on a Concept | All | 2022-09-05 | 2022-09-05 | 0 | 100%
1.5 | Create Directory Structure | Charlie | 2022-09-20 | 2022-09-20 | 0 | 100%
1.6 | Clarify Concept - Fitness Center | All | 2022-09-26 | 2022-09-26 | 0 | 100%
1.7 | Decide on Project Name | All | 2022-09-26 | 2022-09-26 | 0 | 100%
2 | Planning
2.1 | Users - 3 classes | Christina |  |  | 0 | 0%
2.2 | Financial Reports - Z Reports - CashFlow | Christina |  |  | 0 | 0%
2.3 | Inventory - Details - Vendor - TTL | Beesanne |  |  | 0 | 0%
2.3.1 | Services | Erica, Beesanne |  |  | 0 | 0%
2.4 | Shopping Cart - Payment | Olamide |  |  | 0 | 0%
2.5 | Reciepts | Olamide |  |  | 0 | 0%
2.6 | Security | Charlie |  |  | 0 | 0%
2.7 | Sessions Class | Charlie |  |  | 0 | 0%
2.8 | Data Management | Beesanne |  |  | 0 | 0%
2.9 | UI | Erica |  |  | 0 | 0%
2.1 | Email Notifications | Charlie |  |  | 0 | 0%
2.11
3 | Coding and Assembly
3.1 | Creating Database | All |  |  | 0 | 100%
3.2 | Establishing DB Organization | Beesanne |  |  | 0 | 100%
3.2.2 | Review CSS/HTML/JavaScript | Erica |  |  | 0 | 40%
3.3 | Review PHP/MySQL/JavaScript | Charlie, Olamide, Beesanne, Christina |  |  | 0 | 40%
3.3.1 | User Tables | Charlie |  |  | 0 | 30%
3.3.2 | Outline DB Tables | Beesanne |  |  |  | 30%
3.3.3 | Landing Page UI / Frontend | Erica |  |  |  | 20%
3.4.1 | Login - Register System / Backend | Charlie |  |  |  | 30%
3.4.2 | Shopping Cart / Backend | Olamide |  |  |  | 10%
3.4.3 | Financial Reports / Backend | Christina |  |  |  | 10%
| Checkout Page | Olamide |  |  |  | 30%
| User Classes | Christina |  |  |  | 30%
4 | Meetings
4.1 | Webex Group Week 1 | All | N/A | N/A | #VALUE! | 100%
4.2 | Webex Group Week 2 | All | N/A | N/A | 0 | 100%
4.2.1 | Webex Group Week 3 | All | 2022-09-19 | 2022-09-19 | 0 | 100%
9/ | Webex Denizard: UI / General | Erica, All Optional | 2022-09-25 | 2022-09-25 | 0 | 100%
4.3.2 | Webex Group Week 4 | All | 2022-09-26 | 2022-09-26 | 0 | 100%
4.3.3 | Webex Group Week 5 | All | 2022-10-03 | 2022-10-03 | 0 | 100%
| Webex Group Week 6 | All | 2022-10-10 | 2022-10-10 | 0 | 0%
4.3.3 |  |  |  |  | 0